## Introduction
1. Aplikasi yang mau dibuat: Aplikasi Sistem Pulsa dengan MLM
2. Teknologi
| Database: | MSSQL (DEV) & MSSQL LITE (PROD)
| Backend: | C# (Visual Studio)
| DB Framework: | ADO
| Telegram Engine: | PHP
| UI Framework: | PHP (Website Reporting)
| Web Server: | XAMPP
| Repository: | ? (Git)

## Sheet2
Task |  |  | Estimation (hours) |  |  | Status | PIC
|  |  | Optimistic | Average | Pesimistic
Proof Of Concept | [7 empty] | Kesimpulan
| Database Framework |  |  | 0 |  | Done | M | 1 | Database -> My SQL
| Telegram BOT |  |  | 0 |  | Done | M | 2 | Backend -> C#
| Windows Service |  |  | 0 |  | Done | M | 3 | Windows Service
| Web Server XAMPP |  |  | 0 |  | Done | M | 4 | Web Server -> XAMPP
| Source Control |  | 8 | 12 | 16 | In Progress | M, P, A | 5 | Source Control -> Team Foundation Server Online
| Hardware for Server |  | 4 | 6 | 8 |  | M, P, A | 6 | IDE
Business Process | [8 empty] | DB -> Navicat
| 1. Registration |  | 2 | 3 | 4 | Open | BP |  | C# Code -> Visual Studio 2013
| 2. Rewarding |  | 2 | 3 | 4 | Open | BP
|  | Fast Track | 2 | 3 | 4 | Open | BP | To Do List
|  | Matrix | 2 | 3 | 4 | Open | BP | 1 | Setup Environtment | M, P, A
|  | Matahari | 2 | 3 | 4 | Open | BP | 2 | Create TFS Repository | P
|  | Board System | 2 | 3 | 4 | Open | BP | 3 | Follow up document ke Bang Patar | M, P
| 3. Selling Transaction |  | 2 | 3 | 4 | Open | BP
| 4. Telegram Commands |  | 2 | 3 | 4 | Open | BP | Next Meeting
Development | [8 empty] | Rabu, 25 Oktober 2017
| Create Database | [7 empty] | Jam 20.30 - 22.00 (Durasi 1 Jam 30 Menit)
|  | Member | 2 | 2.5 | 3 | Open
|  | Member Status | 2 | 2.5 | 3 | Open |  | Email
|  | Notification Log | 2 | 2.5 | 3 | Open |  |  | pungkas.yoga.k@gmail.com
|  | Reward | 2 | 2.5 | 3 | Open |  |  | adnugrohoo@gmail.com
|  | Product | 2 | 2.5 | 3 | Open |  |  | toshiro89@gmail.com
|  | Transaction Format | 2 | 2.5 | 3 | Open
|  | Transaction Log | 2 | 2.5 | 3 | Open
Backend - Data Access, Codingan layer
|  | Member | 2 | 3 | 4 | Open
|  | Member Status | 2 | 3 | 4 | Open
|  | Notification Log | 2 | 3 | 4 | Open
|  | Reward | 2 | 3 | 4 | Open
|  | Product | 2 | 3 | 4 | Open
|  | Transaction Format | 2 | 3 | 4 | Open
|  | Transaction Log | 2 | 3 | 4 | Open
Logic/Business Process
|  | Fast Track | 12 | 18 | 24 | Open
|  | Matrix | 12 | 18 | 24 | Open
|  | Matahari | 12 | 18 | 24 | Open
|  | Board System | 12 | 18 | 24 | Open
|  | Telegram BOT | 18 | 25 | 32 | Open
Front End
|  | Website Reporting | 24 | 28 | 32 | Open
TOTAL (hours) |  |  | 146 | 205.5 | 265
TOTAL (days) |  |  | 19 | 26 | 34
MARIO | 2 hours per day
PUNGKAS | 2 hours per day
ADHI | 2 hours per day
Testing